Project:	Public Financial Management in the South Caucasus

PN: 	17.2023.4-002.00

Activity:	Assistance to the Ministry of Finance in further implementation of activities under “Strategy on Full-fledged Introduction of Programme Budgeting in Republic of Armenia” – PACKAGE 1: METHODOLOGY AND LEGISLATION

Period:	20.11.2017-30.06.2018

- Background of the Project:

The Caucasus initiative of the Federal Ministry for Economic Cooperation and Development (BMZ) promotes the political and economic cooperation of the South Caucasus republics of Azerbaijan, Armenia and Georgia. The initiative increased not only the country-specific bilateral cooperation, but it also provides them in a regional context. It forms the conceptual clamp and the roof for the German development cooperation with and in the region. Priority areas of cooperation for the Caucasus Initiative are: (a) sustainable economic development, (b) democracy, municipal development and the rule of law, and (c) environment and natural resources.

The Regional Programme “Public Financial Management in the South Caucasus” is implemented by GIZ on behalf of German Development Cooperation in the period of April 1, 2017 till March 31, 2020. The previous programme has been implemented from May 2014 till March 2017. The module objective of the programme is “Subsystems of public finances in Georgia and Armenia approach European and international standards in the fields of result orientation, efficiency and accountability.” The planned activity will be realised in the scope of activities aimed at reaching following outcome - “The Draft Law on Annual Budget 2020 in Armenia, as a main legal document, in programme classification is discussed in the National Assembly of the Republic of Armenia”, measured by relevant output on “Capacities for implementation of results-oriented budgeting are strengthened”.

The services to be rendered by this ToR are deemed to contribute to the above mentioned objectives and the indicator.

- Background Situation

The Government of the Republic of Armenia has made substantial progress in public finance management in recent years. Programme (-based) budgeting reforms were logical part of second generation fiscal reforms launched in 2000s. After adoption of its first long-term socio-economic development strategy (PRSP) the Government of Armenia was facing a challenge of proper reflection of its long-term development strategy in the annual budget. First steps toward that challenge were gradual introduction of the Medium-Term Expenditure Framework (MTEF), followed since 2004 by the introduction of program budgeting (PB) reforms being one of the international trends of managing public spending for achieving better results in producing public goods and/or providing public services.

Till end of 2008 the Government of Armenian was supported through the “Support to programme budgeting introduction in Armenia” Programme of Department for International Development (DfID) of the United Kingdom. During that period the Government made notable progress in initiating program budgeting reforms in Armenia, in particular: first (pilot) methodological guidelines for the introduction of program budgeting were developed and approved, which were piloted in social area ministries (Healthcare, Social Security, Education and Science, and Culture); mainly in above-mentioned ministries, budgets in PB format were developed in line with line-item budgets and presented as an annex in the quarterly distribution of the annual state budget; for some of the budget programmes non-financial quantitative indicators for “policy measures” were developed; and preliminary formats for program budgeting performance reports were developed and approved. Nevertheless only the Ministry of Finance and a few line ministries (mainly social sector) have been able to introduce and adapt the above listed changes. The next step envisaged to widen PB reforms is to cover all line ministries, central agencies and territorial administrations.

Since 2009, the Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) GmbH has agreed to provide technical assistance to the Government of Armenia for further expansion of program budgeting reforms. The technical assistance provided by GIZ in the field of programme budgeting reforms has been covering the following three main directions: (i) provision of technical assistance to the Ministry of Finance of the Republic of Armenia in further methodology development; (ii) enhancement of the capacities of the Ministry of Finance necessary for supporting the state agencies in the transition to programme budgeting; (iii) support the Ministry of Finance of the Republic of Armenia in budgetary legislation reforms cooperating with the National Assembly of the Republic of Armenia.

Since May, 2012, the mentioned assistance in the field of programme budgeting has been envisaged to be provided within the “Public Financial Management in the South Caucasus” (herein after GIZ PFM Programme) regional programme, through involvement of a relevant qualified local consulting company which should continue support to the staff of MoF and other state agencies in transfer to the programme budgeting.

By the end of first phase of GIZ PFM Programme the activities of the First Phase of the PB reform agenda have been finalised by the adoption of Amendments to the Law on Budgetary System prescribing the key elements of the program budgeting system by legislation. Besides of legislation changes, the core emphasis in the support to MOF has been the development of the necessary methodological basis, as well as elaboration of conceptual framework for further implementation of PB reforms, such as coordination with and building the capacities and necessary organisational restructuring of all line ministries, possibilities of transition to a multi-year budgeting, budget programme and indicator system revision etc.

Different assessments done both by GIZ PFM Programme and by other development partners have revealed gaps in coordination and harmonisation of PB reforms with other simultaneous PFM sector reforms such as public sector accounting, treasury, internal and external control and audit reforms, etc.; those reforms should be complementing each other and assure full transition to PB by the given timeframe. Besides, in order to roll-out the PB reforms it is a crucial necessity to scale up capacity building activities especially in line ministries and other state entities. This is proven also by an increased demand and interest of the National Assembly and especially some of the sector committees towards budget drafts and execution reports discussion, with more focus on programmes and performance indicators.

In the framework of further cooperation between Ministry of Finance of the Republic of Armenia and GIZ PFM Programme, and based on the above-mentioned findings, it was agreed to analyse the current state of the PB reforms, reveal the gaps and develop a new detailed strategic action plan for further implementation of reforms. Thus, in the period of October 2014 - April 2015, a thorough analysis of status-quo f PB reforms was done by a team of experts from SIPU International consulting company, and based on it a draft of the PB Strategy and its detailed implementation plan was elaborated and submitted to the Ministry of Finance for its further review and finalisation. On August 13, 2015 the Final PB Strategy and Implementation plan were approved by the Government of Armenia.

The approved strategy envisages activities aiming at finalisation of the main stage of reforms with full-fledge implementation of programme budgeting on the level of State Budget, which means that the State Budget for 2019 will be developed, approved, executed and reported in mainly in PB format. The Strategy envisages also simultaneous conduction of activities in all other relevant PFM reform areas with constant steering, coordination and harmonisation of relevant activities among all stakeholders of the reforms.

According to the agreement between the Ministry of Finance of the Republic of Armenia and GIZ PFM Programme, the PB strategy and its detailed action plan serve as a basis for further cooperation and support to the PB Reforms provided by GIZ on behalf of German Federal Government.

- The Objective of the assignment

Based on the overall objectives and directions of the PB Strategy of the Government of Armenia, the main objective of the current assignment is to support the Ministry of Finance of Armenia in further implementation of certain activities, mainly finalisation of PB methodology and relevant legal framework, envisaged by the PB Strategy and its Detailed Action Plan to be implemented during period of November 2017 – June 2018, aiming at full transition to programme budgeting as a main format of annual state budget to be approved, executed and reported.

- Main Tasks, Expected Deliverables and Deadlines

The main tasks within the assignment will be support to the Ministry of Finance in following (in total up to 145 expert-days):

- Finalisation of the Methodological Manual on Programme Budgeting, which will incorporate following sub-manuals/chapters (up to 85 expert-days):

- Review (wherever necessary, after practical application) and finalisation of already developed and approved sub-manuals/chapters (up to 20 expert-days):

- Methodology on programs and measures in PB format (includes also activities under point 3.3 (partially) and 3.4 of the Implementation Plan of the PB strategy)

- Methodology on performance indicators for programs and measures in PB format (includes also activities under point 3.3 (partially) of the Implementation Plan of the PB

- Methodological instructions on formats for budget documents officially approved and disclosed in PB format by the Parliament, the Government and state agencies

- Alignment of methodological instructions for MTEF and annual budget requests with PB requirements

- General guidelines for costing of budget programs

- Development of new sub-manuals (chapters), envisaged by the PB Strategy (up to 40 expert-days):

- Based on general costing guidelines, provision of guidance/consultancy in elaboration of detailed guidelines on sector-specific costing (wherever necessary, to be agreed with MOF and relevant line ministry(~ies) and/or other governmental institution). Consulting team will not elaborate the sector-specific costing guidelines, but will only provide consultancy/guidance to sector ministries, MOF and relevant experts on general principles of costing in the framework of PB requirements.

- Development of programme classifiers in accordance to PB, as well as elaboration of necessary procedures for alignment of the information collection in PB format with the currently used budget classifications

- Development of detailed instructions on MTEF and annual budget preparation (up to 25 expert-days)

- Conduction of trainings for relevant MOF and line ministries’ staff members on new methodology application (up to 20 expert-days for up to 5 trainings jointly with experts’ teams engaged in revision of all budget programmes (tender packages 2-4))

- Elaboration of the package of amendments and supplements to the RA  Budget System Law (up to 20 expert-days)

- Support in amending and/or supplementing key legal acts supporting the enforcement of the RA Law on Introduction of Changes and /or Amendments to the Law on Budgetary System.

- Small-scale (limited) support to elaboration of instructions/main guiding requirements on following (up to 20 expert-days):

- Guidance/consultancy on establishment of an institute of budget programme responsible officers in the structure of internal financial management and control in state entities (upon request): Consulting team will only provide small-scale consultancy/guidance to MOF and the relevant experts, engaged in FMC related topics, on necessary requirements to be taken into account from PB perspective

- Guidance/consultancy on PB related obligatory parameters for the IT systems used in the whole budgeting cycle (upon request): Consulting team will only provide small-scale consultancy/guidance to MOF and the relevant experts, engaged in IT solutions, on necessary requirements to be taken into account from PB perspective

- Guidance/consultancy on assessment of capacity needs and elaboration of content of trainings modules (upon request): Consulting team will only provide small-scale consultancy/guidance to MOF and the relevant experts, engaged in capacity development measures, on necessary requirements to be taken into account from PB perspective.

It is envisaged that the consulting team during the assignment should closely work with the relevant staff of the Ministry of Finance (in particular staff members form Budget Block and from PFM Methodology Department), though continuous on-job guidance and support, thus assuring gradual transfer of knowledge and capacities to MOF and overall sustainability of PB reforms.

- Reporting and Timetable

During the assignment period 6 reports should be provided – 1 inception, 4 interim and 1 final - on basis of the activities implemented and provided deliverables with following periodicity:

- 1st (Interim) Report – till 12th of December, 2017 – Administrative Report and relevant deliverables for that period

- 2nd (Interim) Report – till 20th of April, 2018 – Second Administrative Report and relevant deliverables for that period

- 3rd (Final) Report – till 25th of June, 2018 – Third (final) Administrative Report and relevant deliverables for that period

All reports (administrative reports and relevant deliverables) should be submitted in English and Armenian languages. All reports should be submitted electronically and in hard-copy versions (1 Armenian version for MoF and 1 English version for GIZ).

Prior to payments, the reports and the deliverables should be presented to and discussed with the Ministry of Finance and GIZ PFM Programme. GIZ should receive final approval from the Ministry of Finance on submitted reports and deliverables as confirmation of services agreed.

Only after that the payments will be processed.

It is envisaged that the activities should be implemented from November 20, 2017 till June 30, 2018.

- Qualification requirements

It is envisaged, that the assignment will be implemented through relevant team of experts of a local consulting company.

The team may have following composition:

- Team Leader / Key Expert

- Experts – at least 2 key experts

Team will work in close cooperation with relevant staff members from the Ministry of Finance of RA and relevant experts of GIZ PFM Programme.

Experts should comply with following requirements to qualification:

Team leader / Key Expert 1

- At least Master Degree or its equivalent level in public finance, economics or related field.

- At least 10 years of experience in public policies and reforms analysis.

- At least 8 years of experience in leading and coordinating teamwork, with proven experience in project formulation and methodology development, experience of similar work in other (including CIS) countries is an asset.

- Proven knowledge of programme budgeting and PFM reforms, including policy-based budgeting, and multi-year planning.

- Fluency in Armenian and English are an essential requirement.

Key Experts

- At least Master Degree or its equivalent level in public finance, economics or related field.

- At least 8 years of experience in public policies and reforms analysis.

- At least 5 years of experience in conducting different assessments on different aspects of public policies and budget programmes, including strategies, polices and projects.

- Proven experience in development and assessment of methodology in the field of budgeting and project design, formulation.

- Proven knowledge and understanding of budgetary system and public financial management issues, including result-oriented budgeting, transparency and budget oversight.

- Fluency in Armenian and English are an essential requirement.

# Footnotes

See RA Government Protocol Decree N 38 on “The Strategy for Full-fledge Introduction of Programme Budgeting in the Republic of Armenia”, adopted on August 13, 2015, https://www.e-gov.am/protocols/item/537/